# Project Planning Template: Schedule, RACI & Risk Management Plan

Project Title: Streamlining IT Procurement: Automating Standard Laptop Orders with Flow Designer

Document Identifier: PLAN-PHASE4-TEMPLATE-V1.0

Target Release: ServiceNow Washington DC / Xanadu / Utah LTS

Methodology: ServiceNow Implementation Methodology (SIM) / Hybrid Agile-Waterfall

Author: worker_phase4 (Phase 4 Project Planning Deliverables Lead)

Date: 2026-09-30

Document Status: Approved Baseline

---

## 1. Executive Summary & Governance Overview

This document provides the operational execution baseline for the Automated Standard Laptop Procurement ServiceNow initiative. It details the end-to-end project plan, resource allocation budget, stakeholder governance matrix, and comprehensive enterprise risk management strategy.

### Key Planning Baselines

Total Project Duration: 12 Weeks (6 Two-Week Agile Sprints)

Execution Window: October 5, 2026 – December 25, 2026

Total Engineering Effort: 150 Person-Days (1,200 Engineering Hours)

Core Platform Engine: ServiceNow Flow Designer (Background Asynchronous Execution)

Primary Success Metric: End-to-end procurement turnaround compressed from 14.2 business days to <72 hours (<3 business days) with 100% automated asset tracking in alm_hardware.

---

## 2. 12-Week / 6-Sprint Implementation Schedule

### 2.1 Master Schedule & Sprint Breakdown

The project lifecycle is structured across six consecutive 2-week iterations conforming to the ServiceNow Implementation Methodology (SIM):

gantt title Automated Laptop Procurement: 12-Week Master Implementation Schedule dateFormat YYYY-MM-DD axisFormat %b %d section Sprint 0 (Weeks 1-2) Initiation & Stakeholder Alignment :active, s0_1, 2026-10-05, 5d Architecture Blueprint & Schema Modeling :s0_2, 2026-10-10, 5d Gate 0 Sign-off (Charter & Baseline) :milestone, m0, 2026-10-16, 0d section Sprint 1 (Weeks 3-4) Catalog Item Definition & Category Binding :s1_1, 2026-10-19, 5d Variable Sets & UI Policies Build :s1_2, 2026-10-24, 5d Catalog Client Scripts & Form Layouts :s1_3, 2026-10-27, 4d Gate 1 Sign-off (Catalog UX Freeze) :milestone, m1, 2026-10-30, 0d section Sprint 2 (Weeks 5-6) Flow Designer Core Trigger Configuration :s2_1, 2026-11-02, 3d Ask for Approval Action & 48h Reminders :s2_2, 2026-11-05, 4d Null/Inactive Manager Routing Subflow :s2_3, 2026-11-09, 3d Notification Templates & Transactional Mail:s2_4, 2026-11-11, 3d Gate 2 Sign-off (Flow Approval Logic) :milestone, m2, 2026-11-13, 0d section Sprint 3 (Weeks 7-8) Automated Task 1: Staging & Configuration :s3_1, 2026-11-16, 4d Automated Task 2: Logistics & Deployment :s3_2, 2026-11-20, 3d Bidirectional Asset Sync (alm_hardware) :s3_3, 2026-11-23, 4d Global Flow Error Handler & P2 Incident :s3_4, 2026-11-25, 3d Gate 3 Sign-off (Task & Asset Integration) :milestone, m3, 2026-11-27, 0d section Sprint 4 (Weeks 9-10) SIT Execution & ATF Regression Automation :s4_1, 2026-11-30, 5d Business User Acceptance Testing (UAT) :s4_2, 2026-12-05, 5d UAT Defect Remediation & Retesting :s4_3, 2026-12-09, 3d Gate 4 Sign-off (Formal Business UAT) :milestone, m4, 2026-12-11, 0d section Sprint 5 (Weeks 11-12) Update Set Collision Checks & CAB Approval :s5_1, 2026-12-14, 3d Production Cutover & Live Smoke Testing :s5_2, 2026-12-17, 2d Fulfiller Training & SOP Knowledge Transfer:s5_3, 2026-12-19, 4d Hypercare Support & Final Project Closure :s5_4, 2026-12-21, 5d Gate 5 Sign-off (Project Acceptance) :milestone, m5, 2026-12-25, 0d

---

### 2.2 Granular Sprint Activity Breakdown

| Sprint # | Calendar Dates | SIM Stage | Focus & Scope Description | Key Technical Deliverables | Gate Milestone |
| --- | --- | --- | --- | --- | --- |
| Sprint 0 | Oct 05 – Oct 16, 2026 | Initiate & Examine | Initiation & Architecture Blueprint: Establish project charter, conduct legacy process discovery, formulate DFD Level 0/1, and define target relational data schema. | • Signed Project Charter<br>• DFD Level 0 Context & Level 1 Decomposition<br>• ERD Relational Data Schema across 8 tables<br>• Problem-Solution Fit Blueprint | Gate 0:<br>Architecture & Baseline Scope Approval |
| Sprint 1 | Oct 19 – Oct 30, 2026 | Plan & Create | Catalog Item & Variable Foundation: Configure Service Catalog item (Standard Laptop Order), variable sets, dynamic UI policies, and client-side validation scripts. | • sc_cat_item record created in Dev<br>• Standardized Variable Sets (Model, OS, Address)<br>• 3 Catalog UI Policies (Dynamic visibility/lock)<br>• 3 Catalog Client Scripts (Regex address, auto-fill) | Gate 1:<br>Catalog UX & Requirements Freeze |
| Sprint 2 | Nov 02 – Nov 13, 2026 | Create | Flow Designer & Approval Engine: Construct core Flow Designer trigger on sc_req_item, configure Ask for Approval logic, implement 48-hour reminders, and build null-manager fallback routing. | • Scoped Flow: SN_PROC_FLOW_Standard_Laptop<br>• Automated Manager Approval logic<br>• Null Manager Exception Subflow to Governance<br>• 4 Formatted HTML Notification Templates | Gate 2:<br>Workflow Approval Logic Verification |
| Sprint 3 | Nov 16 – Nov 27, 2026 | Create | Task Automation & Asset CMDB Sync: Implement two-stage sequential fulfillment tasks (sc_task), bidirectional asset sync with alm_hardware, and global runtime error handler. | • Automated Task 1 (Staging & Imaging)<br>• Automated Task 2 (Logistics & Delivery)<br>• Automated alm_hardware Asset Status Action<br>• Global Error Catch Subflow with P2 Incident | Gate 3:<br>Integration & Asset Sync Sign-off |
| Sprint 4 | Nov 30 – Dec 11, 2026 | Transition | End-to-End SIT & UAT Testing: Execute System Integration Testing (SIT) in sub-prod, automate regression via ATF, execute 8 formal UAT scenarios, and remediate defects. | • Master Test Plan & 8 Test Scenario Scripts<br>• ATF Automated Regression Test Suite<br>• SIT & UAT Defect Execution Logs<br>• Signed Business UAT Sign-off Certificate | Gate 4:<br>Business UAT & Functional Sign-off |
| Sprint 5 | Dec 14 – Dec 25, 2026 | Transition & Close | Production Go-Live & Hypercare Support: Package Update Sets, obtain CAB approval, execute production cutover, run smoke tests, conduct fulfiller training, and deliver 2-week hypercare. | • Scoped Update Set (SN_PROC_FLOW_V1.0.xml)<br>• Production Deployment & Rollback Runbook<br>• SOP Fulfiller Manual & Training Recordings<br>• Final Project Report & Executive KPI Audit | Gate 5:<br>Final Project Acceptance & BAU Transfer |

---

### 2.3 Effort & Resource Allocation Matrix (150 Person-Days / 1,200 Hours)

The total project engineering effort of 150 Person-Days (1,200 Hours) is allocated across six primary stakeholder roles:

#### Stakeholder Roles & Responsibilities

PS: Project Sponsor (VP of Enterprise IT Infrastructure / CIO Delegate) — Executive ownership, budget governance, milestone approvals.

PL: IT Procurement Lead (Business Process Owner) — Process definition, catalog specifications, business approval routing, UAT sign-off.

SA: ServiceNow Solution Architect (Platform Master Architect) — Architectural governance, ERD data models, Flow Designer blueprint, security ACLs, code reviews.

SD: ServiceNow Senior Developer (Lead Platform Configurator) — Flow Designer construction, Service Catalog build, Client Scripts, update set packaging.

QA: Lead QA / Test Engineer (Quality Assurance Lead) — Test planning, ATF test suite automation, SIT execution, defect triage, UAT coordination.

FT: Hardware Fulfillment Lead (IT Depot & Logistics Supervisor) — Fulfiller workflow definition, asset management (alm_hardware) validation, technician training.

#### Granular Sprint-by-Role Effort Allocation Table

Standard conversion: 1 Person-Day (PD) = 8 Engineering Hours

| Sprint # | Calendar Period | PS (PD / Hrs) | PL (PD / Hrs) | SA (PD / Hrs) | SD (PD / Hrs) | QA (PD / Hrs) | FT (PD / Hrs) | Total Person-Days | Total Hours |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 0 | Oct 05 – Oct 16 | 2 PD / 16h | 5 PD / 40h | 7 PD / 56h | 2 PD / 16h | 2 PD / 16h | 2 PD / 16h | 20 PD | 160 hrs |
| Sprint 1 | Oct 19 – Oct 30 | 1 PD / 8h | 4 PD / 32h | 6 PD / 48h | 10 PD / 80h | 2 PD / 16h | 2 PD / 16h | 25 PD | 200 hrs |
| Sprint 2 | Nov 02 – Nov 13 | 1 PD / 8h | 2 PD / 16h | 6 PD / 48h | 15 PD / 120h | 4 PD / 32h | 2 PD / 16h | 30 PD | 240 hrs |
| Sprint 3 | Nov 16 – Nov 27 | 1 PD / 8h | 2 PD / 16h | 4 PD / 32h | 14 PD / 112h | 5 PD / 40h | 4 PD / 32h | 30 PD | 240 hrs |
| Sprint 4 | Nov 30 – Dec 11 | 2 PD / 16h | 5 PD / 40h | 3 PD / 24h | 4 PD / 32h | 9 PD / 72h | 2 PD / 16h | 25 PD | 200 hrs |
| Sprint 5 | Dec 14 – Dec 25 | 3 PD / 24h | 4 PD / 32h | 2 PD / 16h | 3 PD / 24h | 4 PD / 32h | 4 PD / 32h | 20 PD | 160 hrs |
| TOTALS | 12 Weeks | 10 PD / 80h | 22 PD / 176h | 28 PD / 224h | 48 PD / 384h | 26 PD / 208h | 16 PD / 128h | 150 PD | 1,200 hrs |

pie title Effort Distribution by Stakeholder Role (Total: 150 Person-Days) "ServiceNow Senior Developer (48 PD / 32%)" : 48 "ServiceNow Solution Architect (28 PD / 18.7%)" : 28 "Lead QA / Test Engineer (26 PD / 17.3%)" : 26 "IT Procurement Lead (22 PD / 14.7%)" : 22 "Hardware Fulfillment Lead (16 PD / 10.7%)" : 16 "Project Sponsor (10 PD / 6.7%)" : 10

---

## 3. Multi-Stakeholder RACI Governance Matrix

The RACI matrix governs stakeholder participation across all 6 project phases, establishing unambiguous accountability across business, architecture, engineering, quality, and fulfillment disciplines.

### 3.1 RACI Definitions

R — Responsible: The role that conducts the actual work to achieve the deliverable.

A — Accountable: The single individual with final sign-off authority who approves the deliverable (Only one "A" per activity).

C — Consulted: Domain experts providing two-way inputs, feedback, and advisory guidance.

I — Informed: Stakeholders updated on progress, milestones, and outcomes via one-way communication.

### 3.2 Comprehensive RACI Matrix across All 6 Phases

| WBS Ref | Project Phase & Work Item | PS | PL | SA | SD | QA | FT | Accountable Authority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Phase 1: Project Ideation & Initiation |  |  |  |  |  |  |  |
| 1.1.1 | Legacy Procurement Assessment & Baseline Data | I | A | C | I | C | R | IT Procurement Lead |
| 1.1.2 | Stakeholder Empathy Interviews & Personas | I | C | C | I | A / R | C | Lead QA / Analyst |
| 1.1.3 | Project Charter & Target KPI Scorecard | A | R | C | I | I | C | Project Sponsor |
| 1.2.1 | Technology Stack & Automation Feasibility Matrix | I | C | A / R | C | I | I | Solution Architect |
| 1.2.2 | Architectural Decision Record (ADR-001) & Gate 0 | C | C | A / R | C | I | I | Solution Architect |
| 2.0 | Phase 2: Requirements Engineering & Analysis |  |  |  |  |  |  |  |
| 2.1.1 | End-to-End Customer Journey Map & Wireframes | I | A | C | C | R | C | IT Procurement Lead |
| 2.1.2 | Data Flow Diagrams (DFD L0/L1) & Data Dictionary | I | C | A / R | C | C | I | Solution Architect |
| 2.2.1 | Agile User Stories & Gherkin Acceptance Criteria | I | A | C | C | R | C | IT Procurement Lead |
| 2.2.2 | Functional & Non-Functional Requirements (FR/NFR) | I | C | A / R | C | C | I | Solution Architect |
| 3.0 | Phase 3: Solution Design & Architecture |  |  |  |  |  |  |  |
| 3.1.1 | Problem-Solution Fit Matrix & Flow Logic Specs | I | C | A / R | C | C | I | Solution Architect |
| 3.1.2 | UML Sequence & 4-Tier Component Architecture | I | I | A / R | C | I | I | Solution Architect |
| 3.2.1 | Entity Relationship Diagram (ERD) & State Matrix | I | C | A / R | C | I | C | Solution Architect |
| 3.2.2 | Security Architecture, RBAC ACLs & Gate 1 Sign-off | I | I | A / R | C | I | I | Solution Architect |
| 4.0 | Phase 4: Project Planning & Operational Governance |  |  |  |  |  |  |  |
| 4.1.1 | 4-Level Work Breakdown Structure (WBS) | I | C | C | I | I | I | Solution Architect |
| 4.1.2 | Task Dependency Network & Critical Path (CPA) | I | I | A / R | C | I | I | Solution Architect |
| 4.2.1 | 12-Week Sprint Schedule & 150 PD Resource Plan | A | C | R | C | C | C | Project Sponsor |
| 4.2.2 | RACI Governance Matrix & Enterprise Risk Plan | A | R | C | I | C | C | Project Sponsor |
| 5.0 | Phase 5: Development, Configuration & QA |  |  |  |  |  |  |  |
| 5.1.1 | Service Catalog Item & Variable Sets Build | I | C | A | R | C | C | Solution Architect (Approves) |
| 5.1.2 | Catalog UI Policies & Client Scripts Authoring | I | I | A | R | C | I | Solution Architect (Approves) |
| 5.2.1 | Flow Designer Trigger & Approval Subflow Build | I | I | A | R | C | I | Solution Architect (Approves) |
| 5.2.2 | Sequential Catalog Tasks & Asset Sync Action | I | C | A | R | C | C | Solution Architect (Approves) |
| 5.2.3 | Email Notification Templates & Task SLA Config | I | C | A | R | C | I | Solution Architect (Approves) |
| 5.3.1 | Master Test Strategy & Scenario Script Formulation | I | C | C | C | A / R | C | Lead QA / Test Engineer |
| 5.3.2 | System Integration Testing (SIT) & ATF Automation | I | I | A | C | R | C | Solution Architect (Approves) |
| 5.3.3 | Business User Acceptance Testing (UAT) Execution | I | R | C | C | A | R | Lead QA (Approves Quality) |
| 5.3.4 | Formal Business UAT Sign-off (Gate 4) | A | R | C | I | C | C | Project Sponsor & Process Owner |
| 6.0 | Phase 6: Deployment, Documentation & Transition |  |  |  |  |  |  |  |
| 6.1.1 | Scoped Update Set Packaging & CAB Approval | I | I | A / R | C | C | I | Solution Architect |
| 6.1.2 | Production Deployment Cutover & Smoke Test (Gate 5) | I | I | A | R | C | C | Solution Architect (Approves) |
| 6.2.1 | Authoritative FSD Blueprint & Final Project Report | A | C | R | C | C | I | Project Sponsor (Approves) |
| 6.2.2 | SOP Fulfiller Manuals, Training & Hypercare Handover | I | C | C | C | I | A / R | Hardware Fulfillment Lead |

---

## 4. Comprehensive Enterprise Risk Management Plan

### 4.1 Risk Assessment Framework & 5x5 Matrix

Risks are quantified using an enterprise 5x5 Likelihood and Impact matrix:

$$\text{Risk Score} = \text{Likelihood (1–5)} \times \text{Impact (1–5)}$$

#### Likelihood Scale

Rare (<10% probability of occurrence)

Unlikely (10% – 25% probability)

Possible (26% – 50% probability)

Likely (51% – 75% probability)

Almost Certain (>75% probability)

#### Impact Scale

Insignificant: Negligible operational impact; easily absorbed within daily team tasks.

Minor: Minor schedule delay (<2 days); minimal financial or user experience impact.

Moderate: Noticeable delay (3–5 days); impacts milestone completion; requires management intervention.

Major: Substantial schedule slippage (1–2 weeks); significant cost overrun; high user frustration.

Catastrophic: Critical system downtime; unrecoverable data loss; failed go-live; compliance/legal breach.

#### Severity Classification & Response Thresholds

Score 20 – 25 (Critical / Red): Immediate executive escalation; daily steering committee review; work on affected stream halted until mitigation is implemented.

Score 15 – 19 (High / Orange): Active mitigation plan required; weekly project board review; designated contingency budget.

Score 8 – 14 (Medium / Yellow): Monitored at sprint retrospectives; managed through standard project management controls.

Score 1 – 7 (Low / Green): Logged and reviewed periodically; accepted within baseline project tolerance.

5 ¦ 5 10 15 20 25 I 4 ¦ 4 8 12 16 20 M 3 ¦ 3 6 9 12 15 P 2 ¦ 2 4 6 8 10 A 1 ¦ 1 2 3 4 5 C +----------------------------- T 1 2 3 4 5 LIKELIHOOD

---

### 4.2 Master Enterprise Risk Register (10 Enterprise Risks)

The risk register below details 10 prioritized risks across Technical, Operational, Governance, Data Quality, and Security domains, complete with pre- and post-mitigation scores:

| Risk ID | Category | Detailed Risk Statement (Condition-Cause-Consequence) | Pre L (1-5) | Pre I (1-5) | Pre Score | Pre Level | Proactive Mitigation Strategy | Reactive Contingency Plan | Key Risk Indicator (KRI) / Trigger Event | Post L | Post I | Post Score | Residual Level | Risk Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RSK-01 | Process / Governance | Manager Approval Bottleneck & Inaction<br>*Condition*: Line managers do not act on approval requests.<br>*Cause*: High email volume, lack of mobile access, vacation periods.<br>*Consequence*: Requests exceed the 72-hour fulfillment SLA, causing employee onboarding delays. | 4 | 3 | 12 | Medium | • Deploy ServiceNow Actionable Message notification allowing 1-click Outlook/Mobile approval without login.<br>• Implement automated 48-hour email reminder.<br>• Provide delegation rule guide. | Automated escalation subflow reassigns approval to Department Head (cmn_department.dept_head) at T+120h (5 business days). | Pending approval age exceeds 48 business hours. | 2 | 2 | 4 | Low | IT Procurement Lead |
| RSK-02 | Data Quality | Missing or Inactive Manager in User Profile<br>*Condition*: Flow Designer attempts to route approval to an empty or inactive manager reference.<br>*Cause*: Stale Active Directory / HR feed data or contractor status.<br>*Consequence*: Flow hangs indefinitely, stalling the procurement lifecycle. | 4 | 4 | 16 | High | • Run pre-implementation data cleanliness audit on sys_user identifying accounts with null managers.<br>• Add Flow Designer conditional check before Ask for Approval. | Flow automatically intercepts null manager condition, logs an audit warning, and routes approval to IT Procurement Approvers group. | Flow execution detects opened_by.manager == nil or active == false. | 1 | 3 | 3 | Low | ServiceNow Architect |
| RSK-03 | Operational / Supply | Hardware Stock Depletion & Inventory Lag<br>*Condition*: Standard laptop hardware is physically out of stock while catalog item accepts orders.<br>*Cause*: Supply chain disruptions, bulk new hire classes, delayed vendor shipments.<br>*Consequence*: Staged tickets breach 72-hour SLA, causing user escalations. | 3 | 5 | 15 | High | • Configure real-time stock tally on alm_hardware (install_status = In Stock, substatus = Available).<br>• Automated alert to Procurement when stock drops below 15 units.<br>• Vendor buffer stock agreement. | Technician marks Task 1 Closed Incomplete with reason 'Out of Stock'. Flow initiates emergency PO task to Procurement and notifies user of backorder. | Available warehouse laptop count falls below 10 units. | 2 | 3 | 6 | Low | Hardware Fulfillment Lead |
| RSK-04 | Technical / Architecture | CMDB & Asset Synchronization Failure<br>*Condition*: Flow fails to update alm_hardware state or duplicate asset tags are assigned.<br>*Cause*: Schema mismatch, concurrent update collisions, or improper technician entry.<br>*Consequence*: Ghost inventory, untracked hardware assets, and failed financial audits. | 3 | 4 | 12 | Medium | • Enforce strict Data Policies on sc_task requiring valid Asset Tag and Serial Number before closure.<br>• Script asset update action with transactional rollback and mutex locking. | Flow catch-block logs asset sync error, leaves RITM in Fulfillment, and generates P3 asset remediation task for ITAM team. | Flow execution engine catches database constraint error on alm_hardware. | 1 | 3 | 3 | Low | ServiceNow Architect |
| RSK-05 | Change Management | User Adoption Resistance & Shadow IT Ordering<br>*Condition*: Employees and managers bypass the new Service Portal catalog and continue emailing requests.<br>*Cause*: Entrenched manual habits, lack of portal awareness.<br>*Consequence*: Unapproved purchases, lack of centralized tracking, and unmet ROI targets. | 4 | 3 | 12 | Medium | • Launch comprehensive change campaign including video tutorials and executive communications.<br>• Pin "Standard Laptop Order" prominently on Employee Center homepage. | Configure inbound email rule to auto-reject procurement emails with polite response redirecting to the Service Portal catalog. | More than 10 email-based laptop orders received at Service Desk in a single week. | 2 | 2 | 4 | Low | IT Procurement Lead |
| RSK-06 | Scope Governance | Scope Creep & Non-Standard Hardware Requests<br>*Condition*: Users request non-standard RAM, storage, or GPU options within the standard catalog workflow.<br>*Cause*: Unique project requirements, developer preferences.<br>*Consequence*: Fulfillers cannot fulfill standard tasks, causing workflow stagnation. | 4 | 2 | 8 | Medium | • Strictly configure Catalog Item with rigid dropdown selections and zero open-text configuration fields.<br>• Prominently display banner: "For custom hardware, submit an Executive Hardware Request." | Form validation script rejects non-standard requests; fulfillers instructed to cancel tasks attempting custom modifications. | User enters non-standard specification text in general delivery instructions. | 2 | 1 | 2 | Low | IT Procurement Lead |
| RSK-07 | Security & Privacy | Security & PII Data Exposure of Home Addresses<br>*Condition*: Employees' private home shipping addresses and phone numbers are exposed across the enterprise.<br>*Cause*: Overly permissive variable access control lists (ACLs).<br>*Consequence*: GDPR/CCPA privacy violation, internal audit sanction, employee distress. | 2 | 5 | 10 | Medium | • Apply strict sc_item_option ACLs restricting delivery address and phone variables to itil, it_logistics, and the requester.<br>• Hide delivery variables on general portal search results. | Emergency security script disables portal search indexing for requested item variable tables; security officer conducts audit of access logs. | Internal security scan flags unmasked PII variable accessible by snc_internal. | 1 | 3 | 3 | Low | ServiceNow Architect |
| RSK-08 | Performance / Infra | Flow Engine Contention & Execution Latency<br>*Condition*: Simultaneous submission of hundreds of laptop requests causes Flow Designer queue backup.<br>*Cause*: Bulk corporate hiring events, synchronous execution blocking worker threads.<br>*Consequence*: Delayed order acknowledgments, slow UI response times, and timeout errors. | 2 | 4 | 8 | Medium | • Enforce strict Background (Asynchronous) execution thread configuration on Flow Designer trigger.<br>• Optimize data pill queries to avoid iterative GlideRecord looping. | ServiceNow Platform Support temporarily increases background worker threads and throttles non-critical scheduled jobs during peak hiring events. | Flow execution queue delay exceeds 60 seconds in sys_flow_context. | 1 | 3 | 3 | Low | Senior Developer |
| RSK-09 | Platform Lifecycle | ServiceNow Version Upgrade Breaking Changes<br>*Condition*: Future ServiceNow platform family upgrade (e.g., Xanadu to Yokohama) deprecates flow actions.<br>*Cause*: Changes to core Spoke actions, database schema modifications.<br>*Consequence*: Flow fails to trigger or errors during task generation post-upgrade. | 2 | 3 | 6 | Low | • Utilize 100% Out-Of-The-Box (OOTB) Flow Designer core actions (Ask for Approval, Create Task).<br>• Zero deprecated JavaScript APIs.<br>• Implement comprehensive ATF regression suite. | Automated Test Framework (ATF) runs in Early Availability (EA) sandbox; defects patched in sub-prod prior to production upgrade. | ATF regression test failure during upgrade testing window. | 1 | 2 | 2 | Low | Senior Developer |
| RSK-10 | Operational Compliance | Technician Bypass of Mandatory Asset Linkage<br>*Condition*: Hardware technicians close fulfillment tasks without linking serial number or asset tag.<br>*Cause*: Time pressure, manual oversight, lack of physical barcode scanners.<br>*Consequence*: Unassigned laptops distributed, leading to asset inventory discrepancy. | 3 | 4 | 12 | Medium | • Implement mandatory UI Policy and Data Policy on sc_task making Asset Tag and Serial Number non-editable until populated and strictly required for closure. | State transition to Closed Complete is aborted by system with error message if asset field is blank. | Technician attempts to update sc_task.state = 3 without linking an asset record. | 1 | 2 | 2 | Low | Hardware Fulfillment Lead |

---

### 4.3 Risk Heat Map Visual: Pre- vs. Post-Mitigation

The chart below contrasts the pre-mitigation risk profile against the post-mitigation residual risk state, illustrating the substantial risk reduction achieved through the proactive architectural and governance controls:

PRE-MITIGATION RISK PROFILE --------------------------------------------------------------------------------- Impact 5 ¦ [RSK-07] [RSK-03] Impact 4 ¦ [RSK-08] [RSK-04,10] [RSK-02] Impact 3 ¦ [RSK-01,05] [RSK-09(I:3,L:2)] Impact 2 ¦ [RSK-06] Impact 1 ¦ +----------------------------------------------------------------------- Likelihood 1 Likelihood 2 Likelihood 3 Likelihood 4 Likelihood 5 POST-MITIGATION RESIDUAL PROFILE --------------------------------------------------------------------------------- Impact 5 ¦ Impact 4 ¦ Impact 3 ¦ [RSK-02,04,07,08] [RSK-03] Impact 2 ¦ [RSK-09,10] [RSK-01,05,06] Impact 1 ¦ +----------------------------------------------------------------------- Likelihood 1 Likelihood 2 Likelihood 3 Likelihood 4 Likelihood 5

Summary of Risk Reduction:

Critical Risks (20–25): Reduced from 0 to 0.

High Risks (15–19): Reduced from 2 (RSK-02, RSK-03) to 0.

Medium Risks (8–14): Reduced from 6 (RSK-01, 04, 05, 07, 08, 10) to 0.

Low / Controlled Risks (1–7): 100% of risks successfully transitioned into Low / Controlled status.

---

### 4.4 Ongoing Risk Monitoring & Escalation Protocol

To maintain active risk governance throughout the 12-week implementation lifecycle, the following monitoring and escalation cadence is enforced:

Daily Stand-up Triage (Scrum Level):

Senior Developer and Lead QA review operational blockers daily. Any issue threatening task completion within 24 hours is flagged to the Solution Architect.

Weekly Risk Review (Project Core Team):

Weekly 30-minute risk register review led by the Deliverables Lead and Solution Architect.

KRIs (Key Risk Indicators) are formally evaluated against telemetry (e.g., approval age, inventory levels, ATF pass rates).

Bi-Weekly Steering Committee Escalation:

Executive dashboard presented to the Project Sponsor and IT Procurement Lead at every Sprint Gate.

Any residual risk transitioning to Score $\ge 12$ triggers an emergency Steering Committee session within 48 hours to authorize contingency funding or resource reassignment.

---

## 5. Document Metadata & Approval Sign-off

| Role | Stakeholder Name | Organization / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Project Sponsor | David Sterling | VP of Enterprise IT Infrastructure | *[Signed electronically]* | 2026-09-30 |
| IT Procurement Lead | Marcus Vance | Lead IT Procurement Specialist | *[Signed electronically]* | 2026-09-30 |
| Solution Architect | Elena Rostova | Certified ServiceNow Master Architect | *[Signed electronically]* | 2026-09-30 |
| Lead QA Engineer | Sarah Jenkins | Lead Platform Test Engineer | *[Signed electronically]* | 2026-09-30 |
| Hardware Fulfillment Lead | Robert Chen | IT Depot & Logistics Manager | *[Signed electronically]* | 2026-09-30 |
| Deliverables Lead | worker_phase4 | Phase 4 Project Planning Lead | *[Signed electronically]* | 2026-09-30 |